## May-2026
MONTHLY REPORT
DMR SYSTEM
Region |  | EOA |  | Network |  |  | DMR Hytera | [7 empty] | Month | May-2026
Equipment Status
No | Equipment | Normal Status | Current Status | Comments
1 | MSO Server ( Redundant) (DAMMAM) | Operational | Operational
2 | MSO Server ( Main)(RIYADH) | Operational | Operational
3 | Dispatch Server ( Redundant) (DAMMAM) | Operational | Operational
4 | Dispatch Server( Main)(RIYADH) | Operational | Operational
5 | Recording Server ( Main) | Operational | Operational
6 | Recording Server ( Redundant) | Operational | Operational
7 | PABX /PSTN Gatway | Installed/Not Opertional | Not Configured . | Not Configured .
8 | PSS (Primary) | Operational | Operational
9 | PSS (Secondary) | Operational | Operational
10 | MTU 01 (DAMMAM) | Operational | Operational
11 | MTU 02 (DAMMAM) | Operational | Operational
12 | MTU 03 (DAMMAM) | Operational | Operational
13 | MTU 04 (DAMMAM) | Operational | Operational
14 | MTU 01 (RIYADH) | Operational | Operational
15 | MTU 02 (RIYADH) | Operational | Operational
16 | MTU 03 (RIYADH) | Operational | Operational
17 | MTU 04 (RIYADH) | Operational | Operational
18 | MSO Main(DAMMAM) Core Router Huawei AR2204XE (Primary) | Operational | Operational
19 | MSO Main(DAMMAM) Core Router Huawei AR2204XE (Redundant) | Installed/Not Opertional | Not Configured , | Not Configured .
20 | MSO Main(RIYADH) Core Router Huawei AR2204XE (Primary) | Operational | Operational
21 | MSO Main(RIYADH) Core Router Huawei AR2204XE (Redundant) | Installed/Not Opertional | Not Configured , | Not Configured .
22 | MSO Main(DAMMAM) Core Switch Huawei S5720 (Primary) | Operational | Operational
23 | MSO Main(DAMMAM) Core Switch Huawei S5720 (Redundant) | Operational | Operational
24 | MSO Main(RIYADH) Core Switch Huawei S5720 (Primary) | Operational | Operational
25 | MSO Main(RIYADH) Core Switch Huawei S5720 (Redundant) | Operational | Operational
Outages in this Month
No | Equipment/ site | Site Name | Effected Managed Resource | Severity | Alarm Type | Escalation |  | Recovery |  | Escalated for L3 Support |  | Outage Duration | TT Number | TT Status | TT Owner | Comments
[6 empty] | Date | Time | Date | Time | Date | Time
1 | RF Site 30 | Turaif (NEOA) | Repeaters | Major | Repeater#1 - CHU TX Unit VSWR error/CHU PA Shut Down | 08/07/2025 | 05:40 |  |  |  |  | TT in progress | 6233 | Pending | TMD-Jouf | Closed By NG-FO
2 | RF Site 28 | AL-Qurayyat P_P (NEOA) Critical | Repeaters | Major | Repeater#2 - CHU Tx Unit VSWR Error / CHU PA Shut down | 14/07/2025 | 16:35 |  |  |  |  | TT in progress | 6522 | Pending | TMD-Jouf | FMD Coordanate With Contractor To Resolve
3 | RF Site 30 | Turaif (NEOA) | Repeaters | Critical | Repeater#2 - CHU TX Unit VSWR error/CHU PA Shut Down | 24/08/2025 | 09:43 |  |  |  |  | TT in progress | 8116 | Pending | TMD-Jouf | Closed By NG-FO
4 | RF Site 36 | Waad AlShamal (NEOA VSAT ) Critical | Signal and Coverage issue | Major | Indoor Signal Issue at Generation Budling WAD-AL-SHAMAL | 20/10/2025 | 10:53 |  |  |  |  | TT in progress | 10460 | Pending | TMD-Jouf | Project Team
5 | RF Site 30 | Turaif (NEOA) | Repeaters | Critical | CHU#1&CHU2 PA Shutdown , High VSWR | 25/10/2025 | 06:23 |  |  |  |  | TT in progress | 10622 | Pending | TMD-Jouf | FMD Coordanate With Contractor To Resolve
6 | RF Site 28 | AL-Qurayyat P_P (NEOA) Critical | Repeaters | Critical | Repeater#1 - CHU Tx Unit VSWR Error / CHU PA Shut down | 23/02/2026 | 07:48 |  |  |  |  | TT in progress | 15242 | Pending | TMD-Jouf | Esclated to FMD
7 | RF Site 37 | Rafha PP (NEOA) Critical | Repeaters | Major | Hardware faulty,CHU#2 TX Unit low forward power | 10/03/2026 | 10:38 |  |  |  |  | TT in progress | 15859 | Pending | TMD-Jouf | Esclated to FMD
8 | RF Site 35 | Arar (NEOA) Critical | Repeaters | Major | Hardware faulty,CHU#4 TX Unit low forward power | 11/03/2026 | 06:41 |  |  |  |  | TT in progress | 15897 | Pending | TMD-Jouf | Esclated to FMD
9 | RF Site 5 | Ghazlan P_P2 Critical | Repeaters | Major | Hardware faulty,CHU#1 | 20/03/2026 | 02:33 | 06/05/2026 | 05:43 |  |  | 47 days 3 hrs 10 mins | 16262 | Closed | TMD JUBAIL | Repeater Hanged & Restarted
10 | RF Site 1 | Karma S_S (EOA) | Complete Site | Critical | Site Down | 06/05/2026 | 09:33 | 06/05/2026 | 10:04 |  |  | 0 days 0 hrs 31 mins | 49073 | Closed | TMD JUBAIL | Auto Restore
11 | RF Site 15 | Dhahran Central BSP (EOA) | Complete Site | Critical | Site Down | 13/05/2026 | 04:37 | 13/05/2026 | 04:55 |  |  | 0 days 0 hrs 18 mins | 51980 | Resolved | TMD DAMM
12 | RF Site 36 | Waad AlShamal (NEOA VSAT ) Critical | Complete Site | Critical | Site Down | 14/05/2026 | 23:22 | 14/05/2026 | 18:16 |  |  | 0 days 18 hrs 54 mins | 52056 | Closed | TMD ARAR
13 | RF Site 30 | Turaif (NEOA) | Complete Site | Critical | Site Down | 14/05/2026 | 23:22 | 14/05/2026 | 18:16 |  |  | 0 days 18 hrs 54 mins | 52057 | Closed | TMD ARAR
14 | RF Site 17 | Qurayyah Steam P_P Critical | Repeaters | Major | High VSWR Alarm With Repeater CHU#1 | 14/05/2026 | 10:08 |  |  |  |  | TT in progress | 52069 | Pending | TMD-Hassa
15 | RF Site 11 | Jubail NATD (EOA) | IP Link Down | Critical | Link down | 17/05/2026 | 10:34 | 17/05/2026 | 11:16 |  |  | 0 days 0 hrs 42 mins | 52270 | Closed | MPLS-IP | Un-Approved Activity
16 | RF Site 1 | Karma S_S (EOA) | Complete site | Critical | Site Down | 23/05/2026 | 00:43 | 23/05/2026 | 01:10 |  |  | 0 days 0 hrs 27 mins | 52991 | Closed | TMD JUBAIL | Auto Restore
17 | RF Site 1 | Karma S_S (EOA) | Complete site | Critical | Site Down | 23/05/2026 | 09:06 | 23/05/2026 | 09:35 |  |  | 0 days 0 hrs 29 mins | 53012 | Closed | TMD JUBAIL | Auto Restore
NASCO REPRESENTATIVE
Name |  |  | Signature |  |  | Name | Signature | Name | Signature
Jamal Anwar Pasha (Project Manager) | [5 empty] | Monther. A Al-Roeshedy (Applications & Systems Development Division Manager) |  | Turki A. Al Dahash (Unified OT Communications Division Manager)

## GVMetadata (hidden)
GVData | ew0KICAiZG9jSUQiOiAiYjU4NmRkOGMtMGYxNC00Y2Q5LTk2ODQtYTRjZDlkZDM4NWRiIiwNCiAgInRhZ3NldF8wMDRkZWEzM184NzUxXzQzOTlfYTc2ZV85NWYzNzFjYjQxMTlfZGlzdHJpYnV0aW9uIjogIkV4dGVybmFsIiwNCiAgInRhZ3NldF9lMTY0MDlhN18x
GVData0 | NzAwXzQxNTNfOTA5MF8zOTU1YmMyZjBhZThfY2xhc3NpZmljYXRpb24iOiAiQ29uZmlkZW50aWFsIiwNCiAgIkhlYWRlckxlZnQiOiAiIiwNCiAgIkhlYWRlckNlbnRlciI6ICJcdTAwMjZLOEI4MDAwXHUwMDI2MTBDbGFzc2lmaWVkIGFzIENvbmZpZGVudGlhbCBF
GVData1 | eHRlcm5hbCBieSBTRUMgLSAgXHUwNjI3XHUwNjQ0XHUwNjM0XHUwNjMxXHUwNjQzXHUwNjI5IFx1MDYyN1x1MDY0NFx1MDYzM1x1MDYzOVx1MDY0OFx1MDYyRlx1MDY0QVx1MDYyOSBcdTA2NDRcdTA2NDRcdTA2NDNcdTA2NDdcdTA2MzFcdTA2MjhcdTA2MjdcdTA2
ClassificationTagSetId | e16409a7-1700-4153-9090-3955bc2f0ae8
Classification | مقيد / Confidential
ComplianceTagSetId | f14fc1f1-8950-40d5-8a29-45909da947d6
FileId | 2f340699-4422-5e3b-140e-a5b021afebf8
UserId | Anas M. AL-Manaa
TagDateTime | 2024-08-07T04:40:49Z
Distribution | خارجي / External
ClassificationHash | {classification_guid}
ComplianceHash | {compliance_guid}
DistributionHash | {distribution_guid}
GVData2 | MjEgXHUwNjQ1XHUwNjM1XHUwNjQ2XHUwNjQxIFx1MDY0NVx1MDY0Mlx1MDY0QVx1MDYyRiAoXHUwNjJFXHUwNjI3XHUwNjMxXHUwNjJDXHUwNjRBKSIsDQogICJIZWFkZXJSaWdodCI6ICIiLA0KICAiRm9vdGVyTGVmdCI6ICIiLA0KICAiRm9vdGVyQ2VudGVyIjog
GVData3 | Ilx1MDAyNks4QjgwMDBcdTAwMjYxMENsYXNzaWZpZWQgYXMgQ29uZmlkZW50aWFsIEV4dGVybmFsIGJ5IFNFQyAtICBcdTA2MjdcdTA2NDRcdTA2MzRcdTA2MzFcdTA2NDNcdTA2MjkgXHUwNjI3XHUwNjQ0XHUwNjMzXHUwNjM5XHUwNjQ4XHUwNjJGXHUwNjRBXHUw
GVData4 | NjI5IFx1MDY0NFx1MDY0NFx1MDY0M1x1MDY0N1x1MDYzMVx1MDYyOFx1MDYyN1x1MDYyMSBcdTA2NDVcdTA2MzVcdTA2NDZcdTA2NDEgXHUwNjQ1XHUwNjQyXHUwNjRBXHUwNjJGIChcdTA2MkVcdTA2MjdcdTA2MzFcdTA2MkNcdTA2NEEpIiwNCiAgIkZvb3RlclJp
GVData5 | Z2h0IjogIiINCn0=
GVData6 | (end)